## Sheet1
Sprint #2 Backlog
PBI ID | PBI Name | Task ID | Task | Assigned To | Status
1 | Search by Books Name, Author, ISBN, Category | 1.1 | Take in the correct details | Chen & Liam | Completed
|  | 1.2 | GET method from database to return details | Chen Wang | Completed
|  | 1.3 | Relevant information is returned | Chen Wang | Completed
|  | 1.4 | Test Cases are written up | Liam Carnie | Completed
|  | 1.5.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 1.5.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 1.6 | Code is peer reviewed | Dev Team | Completed
|  | 1.7 | All tests pass | Dev Team | Completed
|  | 1.8 | Documentation updated | Liam Carnie | Completed
|  | 1.9 | Integrated into final build | Dev Team | Completed
4 | Allow shop owner/publisher to add/edit/remove his/her uploaded selling registrations | 4.1 | Front end can handle requests towards selling registrations | Sarthak & Khoi | Completed
|  | 4.2 | Database is updated accordingly | Chen Wang | Completed
|  | 4.3 | All relevant fields are returned/updated/provided | Khoi Nguyen | Completed
|  | 4.4 | Test Cases are written up | Liam Carnie | Completed
|  | 4.5.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 4.5.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 4.6 | Code is peer reviewed | Dev Team | Completed
|  | 4.7 | All tests pass | Dev Team | Completed
|  | 4.8 | Documentation updated | Liam Carnie | Completed
|  | 4.9 | Integrated into final build | Dev Team | Completed
7 | Approve a Book to upload to the website (admin) | 7.1 | Check if it is an admin account | Khoi Nguyen | Completed
|  | 7.2.1 | Approval of book generates request | Khoi Nguyen | Completed
|  | 7.2.2 | Denial of book removes it and notifies user | Khoi Nguyen | Completed
|  | 7.3 | Relevant information is posted to database | Khoi Nguyen | Completed
|  | 7.4 | Test Cases are written up | Liam Carnie | Completed
|  | 7.5.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 7.5.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 7.6 | Code is peer reviewed | Dev Team | Completed
|  | 7.7 | All tests pass | Dev Team | Completed
|  | 7.8 | Documentation updated | Liam Carnie | Completed
|  | 7.9 | Integrated into final build | Dev Team | Completed
9 | Allow shop owner/publisher to view Transaction History of sales | 9.1 | Check if it is the relevant account | Sarthak Rungta | Completed
|  | 9.2 | Draw relevant information from database | Sarthak Rungta | Completed
|  | 9.3 | Only the user's book information is returned | Sarthak Rungta | Completed
|  | 9.4 | Test Cases are written up | Liam Carnie | Completed
|  | 9.5.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 9.5.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 9.6 | Code is peer reviewed | Dev Team | Completed
|  | 9.7 | All tests pass | Dev Team | Completed
|  | 9.8 | Documentation updated | Liam Carnie | Completed
|  | 9.9 | Integrated into final build | Dev Team | Completed
21 | Allow Shop Owners to create a book group (shop) | 21.1 | Check if users are shop owners | Khoi Nguyen | Completed
|  | 21.2 | Integrate a joint user database of books | Chen Wang | Completed
|  | 21.3 | Ensure only the data drawn is tied to the group | Chen Wang | Completed
|  | 21.4 | Test Cases are written up | Liam Carnie | Completed
|  | 21.5.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 21.5.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 21.6 | Code is peer reviewed | Dev Team | Completed
|  | 21.7 | All tests pass | Dev Team | Completed
|  | 21.8 | Documentation updated | Liam Carnie | Completed
|  | 21.9 | Integrated into final build | Dev Team | Completed
24 | Seller Search Page: Search for copies associated with provided BookID | 24.1 | Ensure that the book returned is the matching ID | Chen Wang | Completed
|  | 24.2 | Relevant information is drawn from the database | Chen Wang | Completed
|  | 24.3 | Test Cases are written up | Liam Carnie | Completed
|  | 24.4.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 24.4.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 24.5 | Code is peer reviewed | Dev Team | Completed
|  | 24.6 | All tests pass | Dev Team | Completed
|  | 24.7 | Documentation updated | Liam Carnie | Completed
|  | 24.8 | Integrated into final build | Dev Team | Completed