## Sheet1
Sprint #1 Backlog
PBI ID | PBI Name | Task ID | Task | Assigned To | Status
2 | Admin upload a book to database | 2.1 | Check if it is an admin account | Liam Carnie | Completed
|  | 2.2 | Upload new book to database | Liam Carnie | Completed
|  | 2.2.1 | All relevant fields are filled | Dev Team | Completed
|  | 2.2.2 | Database is connected and established | Chen Wang | Completed
|  | 2.3 | Test cases are written up | Liam Carnie | Completed
|  | 2.4.1 | Backend Unit tests written up | Chen Wang | Completed
|  | 2.4.2 | Frontend Unit tests written up | Sarthak | Completed
|  | 2.5 | Code peer reviewed | Dev Team | Completed
|  | 2.6 | All tests pass | Dev Team | Completed
|  | 2.7 | Documentation updated | Liam Carnie | Completed
|  | 2.8 | Integrated into final build | Dev Team | Completed
3 | Registration details validated prior to upload | 3.1 | Check book details are correct before upload | Khoi Nguyen | Completed
|  | 3.1.1 | Relevant fields are filled | Dev Team | Completed
|  | 3.1.2 | Relevant fields do not contain value errors | Dev Team | Completed
|  | 3.2.1 | Backend Unit tests written up | Chen | Completed
|  | 3.2.2 | Frontend Unit tests written up | Sarthak | Completed
|  | 3.3 | Test Cases are written up | Liam Carnie | Completed
|  | 3.4 | Code peer reviewed | Dev Team | Completed
|  | 3.5 | All tests pass | Dev Team | Completed
|  | 3.6 | Documentation updated | Liam Carnie | Completed
|  | 3.7 | Integrated into final build | Dev Team | Completed
14 | Personal page of purchase history | 14.1 | Page is loadable on a device | Derren Chin | In Progress
|  | 14.1.1 | CSS styling is consistent with the rest of the site | Derren Chin | In Progress
|  | 14.1.2 | Everything loads correctly | Sarthak | In Progress
|  | 14.1.3 | Part of the site map | Sarthak | Completed
|  | 14.1.4 | Links and features work correctly | Sarthak | In Progress
|  | 14.2 | Purchase history loads for correct customer | Derren | In Progress
|  | 14.2.1 | Correct transactions show | Sarthak & Khoi | In Progress
|  | 14.2.2 | Transactions are ordered to show recent at top | Sarthak | Incomplete
|  | 14.2.3 | Transactions are able to have information viewed | Sarthak | Incomplete
|  | 14.3 | Test cases are written up | Liam Carnie | Completed
|  | 14.4.1 | Backend Unit tests written up | Chen | In Progress
|  | 14.4.2 | Frontend Unit tests written up | Sarthak | Completed
|  | 14.5 | Code peer reviewed | Dev Team | In Progress
|  | 14.6 | All tests pass | Dev Team | In Progress
|  | 14.7 | Documentation updated | Liam Carnie | In Progress
|  | 14.8 | Integrated into final build | Dev Team | In Progress
15 | Home page items 'About' and 'Contact' | 15.1 | About displays properly and relevant information loads | Sarthak Rungta | Completed
|  | 15.2 | Contact us displays properly and loads | Sarthak Rungta | Completed
|  | 15.3 | CSS styling is consistent with the rest of the site | Sarthak Rungta | Completed
|  | 15.3.1 | Both divs load correct styling | Sarthak Rungta | Completed
|  | 15.3.2 | Links contained are clickable | Sarthak Rungta | Completed
|  | 15.3.3 | All styling loads properly and functionality implemented | Sarthak Rungta | Completed
|  | 15.4 | Test cases are written up | Liam Carnie | Completed
|  | 15.5 | Unit tests are written up | Sarthak Rungta | Completed
|  | 15.6 | Code peer reviewed | Dev Team | Completed
|  | 15.7 | All tests pass | Dev Team | Completed
|  | 15.8 | Documentation updated | Liam Carnie | Completed
|  | 15.9 | Integrated into final build | Dev Team | Completed
16 | Signup and Authentication | 16.1 | Sign up page loads correctly | Khoi Nguyen | Completed
|  | 16.1.1 | Sign up feature takes relevat information | Khoi Nguyen | Completed
|  | 16.1.2 | Sends information to database | Khoi Nguyen | Completed
|  | 16.1.3 | Creates a new user if information is valid | Khoi Nguyen | Completed
|  | 16.1.4 | Throws error if invalid information is provided | Khoi Nguyen | Completed
|  | 16.2 | Sign up page displays consistent CSS styling | Khoi Nguyen | Completed
|  | 16.3 | Test cases are written up | Liam Carnie | Completed
|  | 16.4.1 | Backend Unit tests written up | Chen | Completed
|  | 16.4.2 | Frontend Unit tests written up | Sarthak | Completed
|  | 16.5 | Code peer reviewed | Dev Team | Completed
|  | 16.6 | All tests pass | Dev Team | Completed
|  | 16.7 | Documentation updated | Liam Carnie | Completed
|  | 16.8 | Integrated into final build | Dev Team | Completed
20 | Apply for book selling registration | 20.1 | Apply feature contains relevant fields to fill | Khoi Nguyen | Completed
|  | 20.2 | System checks if the user is an owner or publisher | Khoi Nguyen | Completed
|  | 20.2.1 | If either then allows access to apply | Khoi Nguyen | Completed
|  | 20.2.2 | Otherwise denies access | Khoi Nguyen | Completed
|  | 20.3 | User selects the book(s) | Khoi Nguyen | Completed
|  | 20.4 | System validates the books | Khoi Nguyen | Completed
|  | 20.5 | System checks if the book is already selling | Khoi Nguyen | Completed
|  | 20.6 | Test cases are written up | Liam Carnie | Completed
|  | 20.7.1 | Frontend Unit tests are written up | Sarthak Rungta | Completed
|  | 20.7.2 | Backend Unit tests are written up | Chen Wang | Completed
|  | 20.8 | Code peer reviewed | Dev Team | Completed
|  | 20.9 | All tests pass | Dev Team | Completed
|  | 20.10 | Documentation updated | Liam Carnie | Completed
|  | 20.11 | Integrated into final build | Dev Team | Completed
23 | Login and Authentication | 23.1 | Login page loads correctly | Khoi Nguyen | Completed
|  | 23.1.1 | Login feature takes relevant information | Khoi Nguyen | Completed
|  | 23.1.2 | Draws correct information from database | Khoi Nguyen | Completed
|  | 23.1.3 | Logs in user if information is correct | Khoi Nguyen | Completed
|  | 23.1.4 | Throws error if wrong | Khoi Nguyen | Completed
|  | 23.2 | Login page displays consistent CSS styling | Sarthak | Completed
|  | 23.3 | Test cases are written up | Liam Carnie | Completed
|  | 23.4.1 | Frontend Unit tests are written up | Sarthak | Completed
|  | 23.4.2 | Backend Unit tests are written up | Chen | Completed
|  | 23.5 | Code peer reviewed | Dev Team | Completed
|  | 23.6 | All tests pass | Dev Team | Completed
|  | 23.7 | Documentation updated | Liam Carnie | Completed
|  | 23.8 | Integrated into final build | Dev Team | Completed